## Resumen Sprint
Sprint Metrics — Sprint 2 — BankPortal
Sprint Goal ALCANZADO ¦ 2026-03-30 - 2026-04-10 ¦ v1.1.0
Metrica | Planificado | Real | Variacion | Estado
Story Points | 24 | 24 |  | OK
US completadas | 3 | 3 |  | OK
DEBT resueltas | 2 | 2 |  | OK
Defectos QA | 0 | 0 |  | OK
NCs Code Review | 0 | 0 |  | OK
Gates HITL completados | 4 | 4 |  | OK
VELOCIDAD SPRINT 2 |  |  | 24 SP / sprint

## Items Detalle
Items Sprint 2 — Detalle
ID | Titulo | SP | Tipo | Estado
DEBT-001 | RateLimiterService — Bucket4j + Redis distribuido | 4 | tech-debt | DONE
DEBT-002 | JwtService — JJWT RSA-256 con keypair real | 4 | tech-debt | DONE
US-004 | Desactivar 2FA con confirmacion de contrasena | 5 | new-feature | DONE
US-005 | Auditoria completa e inmutable de eventos 2FA | 5 | new-feature | DONE
US-007 | Suite E2E Playwright — todos los flujos 2FA | 6 | new-feature | DONE
TOTAL | 5 items completados |  |  | 24/24 SP

## Gates HITL
Gates HITL — Sprint 2
Gate | Artefacto | Aprobador | Estado
Sprint Planning | SPRINT-002-planning.md | Product Owner | APPROVED
Code Review | CR-FEAT-001-sprint2-v1.md | Tech Lead | APPROVED
QA Doble Gate | QA-FEAT-001-sprint2.md | QA Lead + PO | APPROVED
Go/No-Go PROD v1.1.0 | RELEASE-v1.1.0.md | Release Manager | APPROVED