## Decisiones S26
ID | Tipo | Título | Fecha | Aprobador | Referencias
ADR-040 | ARCH | Segregación virtual de fondos: reservedAmount NO mueve ledgerBalance | 2026-04-28 | Architect | docs/architecture/sprint-26/HLD-FEAT-024-sprint26.md sec.5
ADR-041 | ARCH | Concurrencia optimista @Version + retry 3x con jitter exponencial | 2026-04-28 | Architect | docs/architecture/sprint-26/LLD-backend-FEAT-024-sprint26.md sec.4
ADR-042 | ARCH | OpenAPI 3.1 vía springdoc como única fuente de verdad de contratos | 2026-04-28 | Architect | HLD sec.7 · cierra DEBT-048..050
ADR-043 | ARCH | Selector multi-cuenta en aportación manual (GET /api/v1/accounts) | 2026-04-28 | Architect + PO | HLD sec.6 · DR-S26-008 · RN-F024-17
DR-S26-007 | DR | B.4 quick patch retry 409 frontend | 2026-05-08 | PO + TL + DV | docs/decisions/DR-S26-007-b4-quick-patch-409.md · DEBT-Q-073
DR-S26-008 | DR | Auth guard fix + multi-cuenta selector | 2026-05-08 | PO + TL + DV | docs/decisions/DR-S26-008-auth-guard-multi-cuenta.md · DEBT-FE-074/075
DAR-S26-01 | DAR | GR-CI-002 diferida formalmente a Sprint 27 | 2026-05-10 | PO + TL + Architect | CMMI-Evidence-Sprint26.docx sec.4 · ADR-S27-XX pendiente
LA-CORE-promo | GOV | GR-SHELL-001 mvn allowlist + TIMEOUT 600s aplicada en SOFIA-CORE | 2026-05-08 | SOFIA Architect | SOFIA-CORE commit 998f430
LA-CORE-pend1 | GOV | GR-SHELL-002 parser shell VAR=val cmd inline (promoción pendiente) | 2026-05-10 | pendiente HITL PO | Step 8b posterior
LA-CORE-pend2 | GOV | GR-FE-002 OBS inline obligatoria escalado a DEBT en Code Review (promoción pendiente) | 2026-05-10 | pendiente HITL PO | Step 8b posterior
DEBT-FE-074 | DEBT | Refactor unificado auth (cierra DEBT-033) prioridad ALTA S27 | 2026-05-08 | PO + TL | docs/backlog/DEBT-073-074-075-sprint26.md
DEBT-Q-073 | DEBT | Refactor 409 handling clean (jitter + logging + endpoints) prioridad MEDIA S27 | 2026-05-08 | TL | docs/backlog/DEBT-073-074-075-sprint26.md
DEBT-FE-075 | DEBT | OBS-005 + E2E UI-driven + prototype-fidelity check prioridad MEDIA S27 | 2026-05-08 | PO + QA + TL | docs/backlog/DEBT-073-074-075-sprint26.md