## Dashboard S21-S23
Métrica | S21 | S22 | S23 | Threshold | Estado S23
Story Points completados | 24/24 | 24/24 | 24/24 | 24/24 | ✅ OK
Tests PASS (%) | 100% | 100% | 100% | 100% | ✅ OK
Cobertura estimada | 88% | 88% | 89% | ≥87% | ✅ OK
Defectos abiertos | 0 | 0 | 0 | 0 | ✅ OK
NCs sprint (bloqueantes) | 0 | 0 | 0 | 0 | ✅ OK
CVE críticos | 0 | 0 | 0 | 0 | ✅ OK
Deudas cerradas sprint | 3 | 3 | 3 | ≥plan | ✅ OK
Code Review APPROVED | Sí | Sí | Sí | Sí | ✅ OK
Smoke tests OK | 17/17 | 17/17 | 9/9 | 100% | ✅ OK
validate-fa-index PASS | PASS | PASS | PASS | PASS | ✅ OK

## Velocidad historica
Sprint | Feature | SP | SP Acum. | Cobertura | Release | Tests Sprint | Defectos
S19 | FEAT-017 Domiciliaciones SEPA | 24 | 449 | 87% | v1.19.0 | 708 | 0
S20 | FEAT-018 Exportación Avanzada | 24 | 473 | 88% | v1.20.0 | 124 | 0
S21 | FEAT-019 Centro Privacidad | 24 | 497 | 88% | v1.21.0 | 65 | 0
S22 | FEAT-020 Préstamos Personales | 24 | 521 | 88% | v1.22.0 | 51 | 0
S23 | FEAT-021 Depósitos a Plazo Fijo | 24 | 545 | 89% | v1.23.0 | 47 | 0

## FA Summary
Métrica FA | Valor | Detalle
Sprints cubiertos | S1..S23 | 23 sprints completos
Total funcionalidades | 86 | FA-001..FA-086
Total reglas de negocio | 198 | Dinámico — nunca hardcodeado (LA-021-01)
validate-fa-index checks | PASS 8/8 | Gates 2b, 3b, 8b — bloqueante
FA docx generado | 73,6 KB | FA-bank-portal-Banco Meridian.docx — python-docx
Funcionalidades S23 nuevas | 8 | FA-079..086 (FEAT-021 Depósitos)
RNs S23 nuevas | +10 | RN-F021-01..10 (depósitos + IRPF + FGD + SCA)
Generador | gen-fa-document.py | Blocking verification: size>10KB + mtime<120s