## Dashboard S24-S26
Métrica | S24 | S25 | S26 | Target | Semáforo
SP delivered | 24 | 24 | 24 | 24 | GREEN
SP acumulados | 569 | 593 | 617 | ≥24/sprint | GREEN
Tests sprint | 25 | 64 | 147 | ≥100 | GREEN
Tests acumulados | 978 | 1042 | 1189 | ≥1000 | GREEN
Cobertura instr | 89 | 89 | 84.3 | ≥80% | GREEN
Cobertura línea | 89 | 89 | 87.2 | ≥85% | GREEN
Defectos prod | 0 | 0 | 0 | 0 | GREEN
NCs | 0 | 0 | 0 | 0 | GREEN
CVE crit/high | 0/0 | 0/0 | 0/0 | 0/0 | GREEN
Gates G-1..G-7 | 7/7 | 7/7 | 7/7 | 7/7 | GREEN
Gate rework | 0 | 1 (BUG-PO) | 3 (B.4+H1+OBS) | ≤1 | YELLOW

## Velocidad
Sprint | Feature | SP | Tests | Cov % | Release
22 | FEAT-020 | 24 | 40 | 87 | v1.22.0
23 | FEAT-021 Depósitos | 24 | 47 | 87 | v1.23.0
24 | FEAT-022 Bizum | 24 | 25 | 89 | v1.24.0
25 | FEAT-023 Mi Dinero (PFM) | 24 | 64 | 89 | v1.25.0
26 | FEAT-024 Objetivos de Ahorro | 24 | 147 | 87.2 | v1.26.0

## FA Analysis
Campo | Valor
Documento | FA-bank-portal-Banco Meridian.docx
Versión | v0.9 (pendiente Step 8b S26 consolidation con RN-F024-16/17)
Funcionalidades total | 108 (S25:100 + 8 nuevas FEAT-024)
Reglas de negocio total | 248 proyectado (S25:231 + 17 nuevas FEAT-024)
Sprints cubiertos | S1-S26
Última actualización SOFIA-CORE | 998f430 (2026-05-08, GR-SHELL-001 mvn allowlist)
LA-CORE pendientes promoción | GR-SHELL-002 · GR-FE-002